## BB Revision Work Plan 2015-16
Susquehanna Greenway Partnership Plan of Work Fiscal Year 2015 - 2016
Goals, Objectives, Tasks |  | # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Desired Outcome | Output Timeframe | Status of Completion | Lead Responsibility | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Staff Costs | Other Costs # Units | Other Costs Cost/Unit | Total Other Costs | TOTAL EXPENSE | DCNR 19 | DCNR 20 | DCNR 21 | DCNR Peer Contracts | ARC | CBC 2015 | CBC 2016 | FPW 2014 | POWR 2016 | PA Humanities Council | Central Susq Commun Fdn | FPW 2015 | Luzerne Fdn | NGOs Civic Orgs | Other Corporate Donations | Williams Transco | PA Realtors Assoc | Individual Donations | Board Member Donations | Program Fees | Mdse. Royalties | Total | Balance Needed | In-Kind Reduction of Cash Expense | In-Kind match of hours/service | In-Kind Source
Education, Advocacy and Promotion | Education, Outreach and Promotion (EOP) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 38970 | 38970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38970 | 0 | 0
| Goal | Build a community of people and partners who share our vision and understand the benefits of the Susquehanna Greenway through outreach and education. Improve their capacity to plan, implement and sustain projects through educational and training programs.
| Objective | 1.1.0 | Strengten Partnerships with Heritage Regions, County Planners, Transportation Planners, State and Federal agencies, land trusts, and non-profit organizations and businesses, to build awareness and support for Susquehanna Greenway projects and to ensure integration of greenway and open-space plans. | County comprehensive plans, greenway and open space plans and Heritage Region Management Plans will incorporate Susquehanna Greenway projects. Improved collaborative partnerships will help to move priority projects to implementation. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 8920 | 8920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8920 | 0 | 0
| Task | 1.1.1 | Partner Collaboration: Participate in Key Conferences: Greenway and Trails Summit, PALTA, etc. Meet with county planners, Conservation Districts and municipal officials in high priority areas to develop strategies for advancing projects. | Improved collaboration to advance Greenway projects |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.1.2 | Strategic Planning: Hold strategic planning meetings with key partners - Board, DCNR, RLOs | Improved collaboration to advance Greenway projects |  |  | Trish, Dee | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.1.3 | Staff Development: Participate EOP-related program training. | Improved Staff development & collaboration skills to advance Greenway projects. |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | EOP | Key Conference Registrations & Fees | [29 empty] | 6 | 100 | 600 | 600 | [21 empty] | 0 | 600
| Dir Cost | EOP | Travel Expenses (Staff Mileage & Misc.) | [29 empty] | 600 | 0.5 | 300 | 300 | [21 empty] | 0 | 300
| Dir Cost | EOP | Meeting Expenses (Catering, Supplies, etc.) | [29 empty] | 40 | 13 | 520 | 520 | [21 empty] | 0 | 520
| Task | 1.1.4 | Advancing Chesapeake Bay Goals: Support the Envision The Susquehanna project, and Chesapeake Conservancy in the development of the Vision for the Susquehanna River. Support Chesapeake Bay Goals & Strategies. |  |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.1.5 | Land Conservation: Work with land trusts and other partners on conserving land within the Greenway corridor |  |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | EOP | Closing Costs for Rozyckie Property at Shickellemy Park Overlook | [29 empty] | 1 | 7500 | 7500 | 7500 | [21 empty] | 0 | 7500
| Objective | 1.2.0 | Create greater awareness for the greenways, trails, recreation and conservation issues and provide the training, tools, and community organizing needed by local communitites to advance greenway projects themselves. | Local partners have the capacity to plan, construct and sustain riverfront parks, walking and biking trails, river accesses, green streets, and rain gardens, in order to stimulate sustainable community development and to allow people to live healthy, more active lives. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 29700 | 29700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29700 | 0 | 0
| Task | 1.2.1 | General Education & Outreach: General communications & information to the public and media; presentations to groups & organizations. | Suppport for Susquehanna Greenway related issues |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.2 | News & Press: Produce 10 electronic newsletters and press releases to inform stakeholders, members about SG news, events, and success stories | Support for Susquehanna Greenway measured by event participation, news coverage, number of volunteers & members |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.3 | SGP Web Site: Expand and maintain content on the Susquehanna Greenway website, emphasizing the PLAN, FUND, and SUCCEED pages. | Local partners are informed about resources to advance greenway projects. |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.4 | Social Media: Conduct social media campaigns | Support for Susquehanna Greenway: measured by event participation, news coverage, number of volunteers & members |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.5 | Photo Library: Manage and maintain the SG Photo Library. |  |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.6 | Tabling Events: Participate in a minimum of 12 tabling events to build awareness for the greenway and engage volunteers and members | Support for Susquehanna Greenway: measured by event participation, news coverage, number of volunteers & members |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | EOP | Travel Expenses Tabling Events | [29 empty] | 1200 | 0.5 | 600 | 600 | [21 empty] | 0 | 600
| Task | 1.2.7 | SG Newsletter Fall 2015: Plan the design & distribution of the SG 2015 Fall Newsletter. |  |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.8 | SG Newsletter Spring 2016: Plan the design & distribution of the SG 2016 Spring Newsletter. |  |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.9 | SG Information Brochure: Plan the design & distribution of the Susquehanna Greenway (tri-fold) Brochure |  |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | EOP | Printing and postage for Fall 2015 Newsletter | [29 empty] | 1 | 4000 | 4000 | 4000 | [21 empty] | 0 | 4000
| Dir Cost | EOP | Printing and postage for Spring 2016 Newsletter | [29 empty] | 1 | 4000 | 4000 | 4000 | [21 empty] | 0 | 4000
| Dir Cost | EOP | Printing Costs for SG Information Brochure | [29 empty] | 1 | 2000 | 2000 | 2000 | [21 empty] | 0 | 2000
| Task | 1.2.10 | Photo Contest: Plan, promote and implement the annual SG Photo Contest. | Local residents, amateur and professional photographers, and children explore Susquehanna Greenway River Towns and recreational assets to capture images of their most Treasured Towns and Landscapes of the Susquehanna Greenway. |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.11 | Traveling Gallery: Plan, promote & implement the Traveling Gallery and gallery opening night events. | Support for Susquehanna Greenway: measured by event participation, news coverage, attendance by members & constituents. |  |  | Kassia/Scarlett | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | EOP | Direct costs for Photo Contest Prizes | [29 empty] | 1 | 1200 | 1200 | 1200 | [21 empty] | 0 | 1200
| Dir Cost | EOP | Direct costs for Photo Gallery Framing | [29 empty] | 1 | 1500 | 1500 | 1500 | [21 empty] | 0 | 1500
| Dir Cost | EOP | Travel Expenses for Photo Gallery installations | [29 empty] | 1000 | 0.5 | 500 | 500 | [21 empty] | 0 | 500
| Dir Cost | EOP | Gallery Event Printing & Postage: Posters, announcements, invites, etc. | [29 empty] | 2 | 1500 | 3000 | 3000 | [21 empty] | 0 | 3000
| Dir Cost | EOP | Gallery Opening Event Expenses: Catering, Supplies, etc. | [29 empty] | 2 | 1500 | 3000 | 3000 | [21 empty] | 0 | 3000
| Task | 1.2.12 | Video Contest: Plan, promote and implement the first annual SG Video Contest | Participants develop, film, and share a "My Susquehanna Greenway Story" video short that depicts their unique personal experiences with the Susquehanna River or river communities. |  |  | Trish, Alice, Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | EOP | Direct costs for video production and prizes | [29 empty] | 4 | 250 | 1000 | 1000 | [21 empty] | 0 | 1000
| Task | 1.2.13 | SG Displays: Design & distribute new Susquehanna Greenway Displays |  |  |  | Zach 2.0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | EOP | Direct cost of displays | [29 empty] | 2 | 750 | 1500 | 1500 | [21 empty] | 0 | 1500
| Task | 1.2.14 | CRM (Client Relationship Management): Manage eTapestry database & Blackbaud services subscription. Perform database updates & data entry. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.15 | Web Platform Support: Manage SGP web site application & platform maintenance. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.16 | SGP Merchandise: Planning & management of the SG Logo Merchandise Sales & Distribution Project. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | EOP | Direct costs of Blackbaud eTapestry database subscription & SGP Web Site domain and maintenance. | [29 empty] | 1 | 5800 | 5800 | 5800 | [21 empty] | 0 | 5800
| Dir Cost | EOP | Direct costs of web site platform & domain: design/development & maintenance services | [29 empty] | 1 | 600 | 600 | 600 | [21 empty] | 0 | 600
| Dir Cost | EOP | Direct costs of SG Logo Merchandise for stock or outreach events. | E-Commerce pages & order processing, COGS, packaging and shipping of orders to be paid by the Merchandise Sales Contractor. Costs will apply when SGP "fills out" order minimums, or places additional orders with items to be "stocked". | [28 empty] | 100 | 10 | 1000 | 1000 | [21 empty] | 0 | 1000
| Task | 1.2.17 | EOP Progress Reporting: Staff collaboration & reporting on objectives, tasks, & outcomes: staff meetings, timesheets, managing/documenting metrics of success & accomplishments, managing project expenditures & deliverables. | SGP Board & Staff, partners & stakeholders will have timely and accurate reporting that shows accountability for project goals, accomplishments & expenditures. |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.18 | EOP Grant Administration: General administration of EOP Program Grant Agreements. | Funders will have timely reporting that shows accountability for project goals, accomplishments & expenditures. | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.2.19 | EOP Work Planning: Development of an annual work plan and resources for next year's EOP Program. Work on EOP-related SGP Strategic Planning. | The plan will guide program initiatives. Reources will be available to run the program |  |  | Erin/Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Objective | 1.3.0 | Advocacy - Increase support for bike/pedestrian trails, water trails, and community green infrastructure initiatives |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0
| Task | 1.3.1 | Policy Committee: Support the SGP Policy Committee and key partners to develop advocacy strategies and position statements on issues of importance to SGP's mission | SGP Board and Staff have an agreed positions to address issues that impact SGP's mission |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.3.2 | Advocacy Conferencing: Participate in the Choose Clean Water Coalition, Renew Growing Greener | Improved ability for SGP to advocate |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.3.3 | Advocacy Outreach: Advocacy Meeting Support, E-Alerts, Letter Campaigns. | Suppport for Susquehanna Greenway related issues |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 1.3.4 | Advocacy Lobbying: Meetings with Legislators. | Suppport for Susquehanna Greenway related issues |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | EOP | Conference Registrations & Fees | [29 empty] | 2 | 100 | 200 | 200 | [21 empty] | 0 | 200
| Dir Cost | EOP | Travel Expenses (Staff Mileage & Misc.) | [29 empty] | 300 | 0.5 | 150 | 150 | [21 empty] | 0 | 150
Susquehanna Greenway Partnership Plan of Work Fiscal Year 2015 - 2016
Goals, Objectives, Tasks |  | # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Desired Outcome | Output Timeframe | Status of Completion | Lead Responsibility | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Staff Costs | Other Costs # Units | Other Costs Cost/Unit | Total Other Costs | TOTAL EXPENSE | DCNR 19 | DCNR 20 | DCNR 21 | DCNR Peer Contracts | ARC | CBC 2015 | CBC 2016 | FPW 2014 | POWR 2016 | PA Humanities Council | Central Susq Commun Fdn | FPW 2015 | Luzerne Fdn | NGOs Civic Orgs | Other Corporate Donations | Williams Transco | PA Realtors Assoc | Individual Donations | Board Member Donations | Program Fees | Mdse. Royalties | Total | Balance Needed | In-Kind Reduction of Cash Expense | In-Kind match of hours/service | In-Kind Source
| River Towns | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6700 | 6700 | 0 | 0 | 0 | 13400 |  |  | 50725 | 64125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64125 | 0 | 0 | 0
| Goal | Build capacity of local partners to plan, construct and sustain riverfront parks, trails, river accesses, green infrastructure, and greenway signs in order to stimulate sustainable community Development | [55 empty] | 0 | 0
| Objective | 2.1.0 | Support SGP River Towns Committee & the River Towns Program to identify and prioritize the relevant needs of our communities and program | The committee will develop strategies and program recommendations to improve SGPs impact in its River Towns |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
| Task | 2.1.1 | River Towns Committee: Convene a minimum of 2 meetings, conference calls or webinars with River Towns Committee | The committee will be engaged with the River Town process and contribute new ideas for its direction forward |  |  | Zach 2.0, Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.1.2 | River Towns Program Manual: Updates/revisions to the River Towns Manual with Team officer descriptions; new Peer Grant SOWs, new Year 1 Report Format; develop semi-annual reporting mechanism | Communities have more specific information and expectations for what the River Town Team will achieve and their role vs SGP's role. |  |  | Scarlett | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | RT | Graphic Design & Printing for revision of the River Towns Program Manual | [29 empty] | 20 | 20 | 400 | 400 | [21 empty] | 0 | 400
| Task | 2.1.3 | Partner Collaboration: Participate in Key Conferences. Meet with county planners, Conservation Districts and municipal officials in high priority areas to develop strategies for advancing projects. | Improved collaboration to advance Greenway projects |  |  | Zach 2.0, Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.1.4 | Staff Development: Participate in River Towns related program training. | Improved Staff development & collaboration skills to advance Greenway projects. |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | RT | Conference and training Registrations & Fees | [29 empty] | 6 | 100 | 600 | 600 | [21 empty] | 0 | 600
| Task | 2.1.5 | River Towns Promotion: Generate articles, success stories, profiles, etc., for publicity & promotion of RT work in SGP newsletters, website, and outreach events. | River Towns will be recognized as a regional asset which attracts visitors and investment. Communities are seen as destinations instead of a point. |  |  | Scarlett | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.1.6 | River Towns Progress Reporting: Staff collaboration & reporting on objectives, tasks, & outcomes: staff meetings, timesheets, managing/documenting metrics of success & accomplishments, managing project expenditures & deliverables. | SGP Board & Staff, partners & stakeholders will have timely and accurate reporting that shows accountability for project goals, accomplishments & expenditures. |  |  | Scarlett | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.1.7 | River Towns Grant Administration: General administration of RT Program Grant Agreements. | Funders will have timely reporting that shows accountability for project goals, accomplishments & expenditures. |  |  | Zach 2.0, Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.1.8 | River Towns Work Plan: Development of an annual work plan and resources for next year's RT Program. Work on RT-related SGP Strategic Planning. | The plan will guide program initiatives. Reources will be available to run the program |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Objective | 2.2.0 | Y1 River Towns: Assist 4 communities to become designated as SGP River Towns and work collaboratively with each community on environmentally sound revitalization strategies (2 through Peer Grant finding) | 4 communities will be identified as SGP River Towns which will make them more visible throughout the greenway and attract investment and visitors |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9800 | 9800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9800 | 0 | 0
| Task | 2.2.1 | River Town Designation: Provide assistance to 4 communities who are ready and willing to begin the River Town designation process. In each community, coordinate one outreach meeting, with local leaders and prospective river town team members, on the benefits of greenways, the Susquehanna Greenway River Town Program, and the RT designation process. In each community, facilitate River Town designation. | Communities will understand the benefits that the RT program offers and begin to identify potential demonstration projects. Communities will have a diverse River Town Team made up of local leaders. |  |  | Zach 2.0, Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.2.2 | River Town Visioning: In each designated River Town, facilitate a series of 4 meetings for community visioning, and project identification (16 total meetings). | Communities will benefit from a clear vision and report containing priority projects for future progress |  |  | Zach 2.0, Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.2.3 | River Town Conceptual Plan: In each designated River Town, facilitate the creation of a Year 1 - River Town Conceptual Plan that details the public process, community input, values, vision and project priorities. (4 total reports) | Community will complete projects efficiently with a clear prioritized focus and will become a highly visible SGP River Town |  |  | Scarlett | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.2.4 | River Town Project Tech. Assistance: In each designated River Town, assist the community in selecting one large-scale priority project for implementation by the municipality and one priority project to be implemented by community volunteers. | Community will be able to coordinate funding and implementation of demonstration project |  |  | Zach 2.0, Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | RT | Printing for Conceptual Plans for 4 Communities. | [29 empty] | 4 | 200 | 800 | 800 | [21 empty] | 0 | 800
| Dir Cost | RT | River Town signs, Double-Side w Frame, for 4 communities | Communities are identified as River Towns and the RT Teams have tools for community engagement | [28 empty] | 4 | 1800 | 7200 | 7200 | [21 empty] | 0 | 7200
| Dir Cost | RT | Travel Expenses (Staff Mileage & Misc. for local meetings with Year 1 Towns.) | [29 empty] | 600 | 0.5 | 300 | 300 | [21 empty] | 0 | 300
| Task | 2.2.5 | Williamsport Civic-Engagement Project: All phases and tasks as defined in the grant application PA Humanities Pre-Work Civic Engagement Project for Williamsport, and the SOW of peer grant match funding for this project. |  |  |  | Alice, Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | WCEP | Printing & Supplies for Williamsport Civic Engagement Project | [29 empty] | 1 | 200 | 200 | 200 | [21 empty] | 0 | 200
| Dir Cost | WCEP | Meeting & Conferencing Expenses (Telephone, Supplies, etc.) for Williamsport Civic Engagement Project | [29 empty] | 12 | 25 | 300 | 300 | [21 empty] | 0 | 300
| Dir Cost | WCEP | Travel Expenses (Staff Mileage & Misc.) for Williamsport Civic Engagement Project | [29 empty] | 1200 | 0.5 | 600 | 600 | [21 empty] | 0 | 600
| Task | 2.2.6 | Selinsgrove Project: All phases and tasks as defined in the specific Peer Project SOW for Selinsgrove. |  |  |  | Trish, Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | PTPP | Printing & Supplies for Peer Consulting Project | [29 empty] | 1 | 200 | 200 | 200 | [21 empty] | 0 | 200
| Dir Cost | PTPP | Travel Expenses (Staff Mileage & Misc.) for Peer Consulting Project | [29 empty] | 400 | 0.5 | 200 | 200 | [21 empty] | 0 | 200
| Objective | 2.3.0 | Y2/Y3 River Towns: Provide continued assistance to Year 2 and Year 3 River Town Communities through project support, funding identification, grant administration, and project implementation. | Communities will continue to build local capacity to complete demonstration projects and will be able to move forward with less SGP assistance on future projects. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 6200 | 6200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6200 | 0 | 0
| Task | 2.3.1 | River Town Tech. Assistance: Assist SGP River Towns with planning and implementing priority projects from their community visioning meetings (Jersey Shore and Lock Haven will be part of pilot project on Asset Based Entrepreneurial Development). Identify River Town Team needs and assist with additional resources on funding or training. | Community will learn and gain local capacity through SGP's assistance and training/workshop opportunities. River Town Teams will become able to take on more projects with less outside help. |  |  | Zach 2.0, Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.3.2 | River Town Implementation Plans: Create 5-Year Community Greenway Implementation Plans |  |  |  | Zach 2.0, Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | RT | Graphic Design & Printing for Implementation Plans & Maps for 4 Communities. | [29 empty] | 4 | 1200 | 4800 | 4800 | [21 empty] | 0 | 4800
| Dir Cost | RT | Travel Expenses (Staff Mileage & Misc. for local meetings with Year 2 and 3 Towns.) | [29 empty] | 600 | 0.5 | 300 | 300 | [21 empty] | 0 | 300
| Task | 2.3.3 | Renovo Peer Consulting Project: Provide Peer to Peer Consulting & Planning for Renovo. | Greenway projects will be scoped and advanced |  |  | Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.3.4 | Jersey Shore Peer Consulting Project: Provide Peer to Peer Consulting & Planning for Jersey Shore. | Greenway projects will be scoped and advanced |  |  | Trish, Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.3.5 | Montgomery Peer Consulting Project: Provide Peer to Peer Consulting & Planning for Montgomery. | Greenway projects will be scoped and advanced |  |  | Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.3.6 | Lock Haven Peer Consulting Project: Provide Peer to Peer Consulting & Planning for Lock Haven. | Greenway projects will be scoped and advanced |  |  | Alice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | PTPP | Graphic Design & Printing for Peer Consulting Projects. | [29 empty] | 4 | 200 | 800 | 800 | [21 empty] | 0 | 800
| Dir Cost | PTPP | Travel Expenses (Staff Mileage & Misc. for Peer Consulting Projects.) | [29 empty] | 600 | 0.5 | 300 | 300 | [21 empty] | 0 | 300
Goals, Objectives, Tasks | Objective | 2.4.0 | Conduct Asset-Based Entrepreneurial Development (ABED) Project in Clinton and Lycoming Counties. | A collaborative partnership is formed with The Progress Fund, SBDC, Lock Haven University, Clinton County Economic Partnership, Williamsport-Lycoming Chamber of Commerce and the River Towns along the Susquehanna that will foster entrepreneurial development and measure its impact on the local economy. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 16200 | 16200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16200 | 0 | 0 | 0
| Task | 2.4.1 | ABED Research & Development: Research and Design Community Assessments & User Surveys (3) - SGP will lead a collaborative effort to design community assessment methodology and user survey instruments to identify the unmet needs of residents and visitors wanting to explore the recreational/historical/cultural assets of participating communities. | Assessment and survey tools will be developed |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.4.2 | ABED Assessments & Surveys: SGP will lead the community assessment process and user surveys in (3) communities, with the assistance of a paid consultant (Progress Fund) | Community assets and unmet needs will be identified |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | ABED | Direct Cost of ABED Consultant Services & Expenses. | [29 empty] | 6 | 700 | 4200 | 4200 | [21 empty] | 0 | 4200
| Task | 2.4.3 | ABED Data Analysis/ Action Plan Phase 1: Analyze Assessment and Survey Results and Formulate a Draft Action Plan - SGP will work with Progress Fund, LHU, and Visitors Bureaus to analyze community assessment and user survey data and create the first part of the Action Plan, including break-out chapters and signage planning for each community. | A Draft Action Plan will help to engage partners in finding solutions to address unmet needs |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.4.4 | ABED Workshop #1 - Plan and conduct a workshop on the overall topic of Nature-Based Placemaking for all (3) communities to review assessment and survey results, and signage plans. Plan educational sessions by PA Downtown Center on (NBP) and success stories in PA Wilds and Great Allgheny Passage ; break-out sessions for each of the (3) communitiesto develop action strategies; general session to develop action strategies for Clinton & Lycoming counties. | Key community leaders understand the economic impact that can be derived from Nature-based placemaking |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | ABED | Direct Costs for Workshop #1 - Catering, supplies, facilities | [29 empty] | 1 | 4000 | 4000 | 4000 | [21 empty] | 0 | 4000
| Task | 2.4.5 | ABED Action Plan Phase 2: SGP will develop (1) Action Plan based on the findings of the assessments, user surveys, & input from the workshop, and will include recommendations for partnerships and business finance, & attraction strategies to foster business start-ups, that will meet needs that have been identified. Action Plan will have break-out chapters for each of the (3) communities, as well as for Clinton & Lycoming counties. | Key partners will be engaged in creating the and implementing the Action Plan to spur entrepreneurial development |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.4.6 | ABED Workshop #2 - Plan and conduct a workshop for all (3) communities to present the Action Plan with educational sessions on successful implementation strategies for attracting business start-ups that will help address unmet needs. Break-out sessions for each community to work on implementation strategies. General session for overall multi-county strategies. | Community leaders and key partners will take ownership for implementation strategies. |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | ABED | Direct Costs for Workshop #2 - Catering, supplies, facilities | [29 empty] | 1 | 4000 | 4000 | 4000 | [21 empty] | 0 | 4000
| Task | 2.4.7 | ABED Action Plan Phase 3 (Final): Finalize the SG Asset Based- Entrepreneurial Action Plan - with break-out chapters for each of the (3) communities, as well as for both counties. | Key partners will be engaged in creating the and implementing the Action Plan to spur entrepreneurial development |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.4.8 | ABED Workshop #3- Plan and conduct a workshop for all (3) communities and entrepreneurs on Starting a Successful Nature/Cultural Based Business | Entrepreneurs will be provided technical assistance on writing sound business plans and financing options for small business. |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | ABED | Direct Costs for Workshop #3- Catering, supplies, facilities | [29 empty] | 1 | 4000 | 4000 | 4000 | [21 empty] | 0 | 4000
| Dir Cost | ABED | Travel Expenses (Staff Mileage & Misc.) for ABED Project | [29 empty] | 800 | 0.5 | 400 | 400 | [21 empty] | 0 | 400
| Objective | 2.5.0 | Promote the Susquehanna Greenway and Improve User Experience through Signage. | Communities will understand that they are part of a much larger greenway system |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0
| Task | 2.5.1 | Visual Connections: Identification of new signage examples that have been implemented throughout the greenway, and updates to the signage guidelines, both in hardcopy and on the website. | New signs such as trail blazes, park signage, and interpretive panels will become more visible and numerous throughout greenway |  |  | Zach 2.0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.5.2 | Signage Technical Assistance: Assist River Towns with design and fabrication of Susquehanna Greenway signage for their communities. | SGP will work with communities to design, place, and record locations of signs and provide assistance in order signs to the correct specifications |  |  | Zach 2.0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.5.3 | Signage Promotion: Generate articles, web site content, etc., for publicity & promotion of the SG Signage Guidelines in newsletters, on website, and at outreach events. | Communities will find new opportunities for signage applications and form new relationships with the SGP through its technical assistance |  |  | Scarlett | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | RT | Travel Expenses (Staff Mileage & Misc. Expenses for signage projects) | [29 empty] | 300 | 0.5 | 150 | 150 | [21 empty] | 0 | 150
| Objective | 2.6.0 | Volunteer Program Y2: Conduct Year Two of the Volunteer Pilot Program to recruit, train and engage volunteers in local greenway projects and events | Successful training methods and materials will be developed and a corps of 60 volunteers will be trained |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6700 | 6700 | 0 | 0 | 0 | 13400 |  |  | 7200 | 20600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20600 | 0 | 0
| Task | 2.6.1 | Volunteer & Ambassador Program Leadership & General Support by AmeriCorps Volunteers | The talents/time/resources of volunteers are engaged to advance the Susquehanna Greenway. |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6700 | 6700 |  |  |  | 13400 |  |  | 0 | 13400 | [21 empty] | 0 | 13400
| Task | 2.6.2 | Volunteer Program Redevelopment Pt. 1: Work with SGP staff to re-focus the Volunteer Program on the River Towns where we are working, and to identify the training needs for Volunteers and SG Ambassadors. | Volunteers are working to complete projects that have been identified in their community's Year 1 Report and 5-Year Implementation Plan |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.3 | Volunteer Program Redevelopment Pt. 2: Work with NPS/CBGN, DCNR, Penn State Master Gardener Program and Conservation Districts to create training tools and a management plan for Volunteer Stewards and SG Ambassadors. | Key partners are providing their expertise in developing effective training materials and methods, as well as a management plan that they are engaged in. |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.4 | SG Ambassador Program Development: Develop training, materials & tools specialized to the SG Ambassadors. |  |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.5 | SG Ambassador Training & Management: Train a group of SG Ambassadors to assist with tabling events and community outreach. Provide ongoing management & maintenance of the Ambassador Program & the SG Ambassadors. | A Corps of Susquehanna Greenway Ambassadors are engaged in outreach and tabling events |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.6 | General Volunteer Training & Management: Provide training and ongoing management of Volunteers working on constituent data, events, photography, etc. |  |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.7 | Volunteer Greenway-Project Community Engagement: Engage three communities (e.g. Berwick, Danville, Lewisburg) for Year 2 of an on-the-ground volunteer program, include Master Gardeners, as well as students from Bloomsburg and Bucknell Universities. | Borough Council and the Public Works Departments of these communities are engaged in working with volunteers |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.8 | Volunteer Greenway-Project Recruitment: Conduct recruitment campaign to engage a minimum of 60 volunteers in 3 communities (~20 per community/section) | 60 Volunteers are engaged in creating and maintaining greenway projects |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.9 | Volunteer Greenway-Project Training: Conduct three training sessions for volunteers on green infrastructure, rain gardens, rain barrels and riparian buffers. Record session and post to website for those unable to attend and future volunteer recruits. | 60 SGP Volunteers have the training they need to safely complete greenway projects in an environmentally sensitive manner |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.10 | Volunteer Greenway-Project Plans: Generate Conceptual Renderings and Site Plans for 3 projects | Demonstration projects are clearly planned and material lists allow for the procurement of items |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.11 | Volunteer Greenway-Project Work Days: Organize & conduct 15 work days (5 days for each community/section). Record volunteer work data (time, mileage, direct expense donated) | River, trail and park improvement projects are completed |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.12 | Volunteer Greenway-Project Impact Reports: Draft one impact report by each group, with recommendations for next priority projects, and ways to make the Volunteer Program more effective. Plan and organize 3 meetings (1 per community) to identify next steps and projects, and to finalize each impact report. | Impact of project is provided to funders. We make changes to improve Year 2 of the pilot project |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | RT/VP | Direct Costs to produce Training Materials: printing, supplies. | [29 empty] | 80 | 10 | 800 | 800 | [21 empty] | 0 | 800
| Dir Cost | RT/VP | Direct Costs of Construction materials for 3 Demonstration Projects - planting materials, gloves, shovels, rakes, bags, seeds and supplies | Three demonstration projects are completed and the volunteers have the experience to do more projects | [28 empty] | 3 | 1500 | 4500 | 4500 | [21 empty] | 0 | 4500 |  |  | Churches and municipalities
| Dir Cost | RT/VP | Volunteer Program Travel Expenses (Staff Mileage & Misc.) | [29 empty] | 3000 | 0.5 | 1500 | 1500 | [21 empty] | 0 | 1500
| Dir Cost | RT/VP | Volunteer Program Meeting Expenses (Catering, Supplies, etc.) | [31 empty] | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.6.13 | Volunteer & Ambassador Recognition & Promotion: Plan, implement & promote Susquehanna Greenway Recognition Awards, and Recognition Events, for Volunteers, Ambassadors, River Towns and Businesses. |  |  |  | Bridget | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | RT/VP | Direct costs for Recognition Awards | [29 empty] | 4 | 100 | 400 | 400 | [21 empty] | 0 | 400
| Dir Cost | RT/VP | Recognition Event Expenses (Catering, Supplies, etc.) | [31 empty] | 0 | 0 | [21 empty] | 0 | 0
| Objective | 2.7.0 | SGTA Project: Provide Technical Assistance to Improve Bike and Pedestrian Trails and to Support the Formation of a Multi-County Greenway and Trail Authority | Improved coordination among transportation planners. local partners, county planners and state agencies to make communities more walkable and bikeable and to expand the network of bike and pedestrian trails along the Susquehanna River. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10175 | 10175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10175 | 0 | 0
| Task | 2.7.1 | SGTA Project Development: Incorporate methodology to conduct community bike/ped audits into the River Towns Program and develop format for audit report findings. Engage transportation planners. | Municipal leaders will understand how to create safer communities for walking and biking. |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.7.2 | SGTA Project Technical Assistance: Provide technical assistance for bike/ped/river access projects, not within River Towns we are currently working with. |  |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.7.3 | SGTA Partner Collaboration: Convene and meet with transportation planners to develop strategies for securing more funding for bike and pedestrian trails along the Susquehanna River, and build a collaborative partnership focused on creating 500 miles of interconnected trails. | Engagement of local and regional transportation planning organizations, state and federal agencies in funding priority trails segments toward the goal of 500 miles of trails along the Susquehanna Greenway. |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.7.4 | SGTA Project Data Analysis: Gather and analyze data on existing and planned trails, trail gaps and community parks as first step of creating Susquehanna Greenway Bike/Ped/River Access Plan in Columbia, Montour, Northumberland, Union and Snyder counties. |  |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | SGTA | Contract with transportation planner to develop Phase I of draft bike and pedestrian plan | Phase I of Plan will be complete which will include: Inventory, Challenges and Opportunities. | [28 empty] | 1 | 10000 | 10000 | 10000 | [21 empty] | 0 | 10000
| Task | 2.7.5 | SGTA Project County Outreach: Convene four meetings with potential SGTA Member Counties to present Phase I Plan findings. | Secure support for key leaders to form the Authority |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.7.6 | SGTA Project: Authority Implementation Planning: Conduct three meetings to form SGTA Steering Committee and develop Draft Five –Year Implementation Strategy, with list of candidate projects derived from the respective county’s Greenways and Open Space Plans. | SGTA is Steering Committee is formed and a draft implementation plan is written and accepted by prospective member counties. |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.7.7 | SGTA Project: Authority Co-Op Agreements: Secure signed inter-governmental cooperation agreement by a minimum of two counties. | Multi-County Greenway and Trail Authority is officially formed |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
Education, Advocacy and Promotion | Task | 2.7.8 | SGTA Project: Authority Member Assistance: Assist Member Counties with application to DCNR for Circuit Rider position to support hiring of Executive Director. Secure member county pledge of match required. | Base funding to get a director for Authority is secured. |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 2.7.9 | SGTA Project: Authority 5-Year Plan: Assist new Authority with finalizing five-year implementation plan. | Prioritized trail projects are advanced more quickly and cost effectively |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | SGTA | SGTA Office Expenses (TeleConferencing, Printing) for 7 Meetings | [29 empty] | 20 | 5 | 100 | 100 | [21 empty] | 0 | 100
| Dir Cost | SGTA | SGTA Travel Expenses (Staff Mileage & Misc.) for 7 Meetings | [29 empty] | 150 | 0.5 | 75 | 75 | [21 empty] | 0 | 75
| Dir Cost | SGTA | SGTA Meeting Expenses (Catering, etc.) for 7 Meetings | [29 empty] | 0 |  | 0 | 0 | [21 empty] | 0 | 0
Susquehanna Greenway Partnership Plan of Work Fiscal Year 2015 - 2016
Goals, Objectives, Tasks |  | # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Desired Outcome | Output Timeframe | Status of Completion | Lead Responsibility | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Staff Costs | Other Costs # Units | Other Costs Cost/Unit | Total Other Costs | TOTAL EXPENSE | DCNR 19 | DCNR 20 | DCNR 21 | DCNR Peer Contracts | ARC | CBC 2015 | CBC 2016 | FPW 2014 | POWR 2016 | PA Humanities Council | Central Susq Commun Fdn | FPW 2015 | Luzerne Fdn | NGOs Civic Orgs | Other Corporate Donations | Williams Transco | PA Realtors Assoc | Individual Donations | Board Member Donations | Program Fees | Mdse. Royalties | Total | Balance Needed | In-Kind Reduction of Cash Expense | In-Kind match of hours/service | In-Kind Source
| Water Trails | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5100 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | 0 | 0
| Goal | Improve and promote the Susquehanna River Water Trails | [56 empty] | 0
| Objective | 3.1.0 | Facilitate collaboration among all the Susquehanna Water Trail Managers and work to develop system-wide programs to promote and enhance the water trails. | Foster environmental stewardship and sustainable economic development by facilitating and promoting the safe use and interpretation of the Susquehanna River Water Trail system. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4050 | 4050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4050 | 0 | 0
| Task | 3.1.1 | Water Trails Committee: Convene 2 meetings of the SG Water Trails Committee. Perform task & admin. support to the Committee & committee meetings. | Identify priority projects and programs, as well as to exchange successful practices among Susquehanna Water Trail Managers, CBGN, PFBC, and DCNR. |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 3.1.2 | Partner Technical Assistance: Provide technical assistance to local partners. | Local partners will create and enhance river access, and develop water trail signage to interpret and improve the visitor experience. |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 3.1.3 | General Water Trails Outreach: Outreach with the public and media on water trails issues and general questions. |  |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | [22 empty] | 0
| Task | 3.1.4 | Partner Collaboration: Participate in Key Conferences. Meet with county planners, Conservation Districts and municipal officials in high priority areas to develop strategies for advancing projects. | Improved collaboration to advance Greenway projects |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 3.1.5 | Staff Development: Participate in Water Trails-related program training. | Improved Staff development & collaboration skills to advance Greenway projects. |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 3.1.6 | Capt John Smith NHTA Council: Participate in the Capt John Smith National Historic Trail Advisory Council | Improved collaboration with NPS for improving Susquehanna River Water Trails |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | WT | Conference and training Registrations & Fees | [29 empty] | 3 | 100 | 300 | 300 | [21 empty] | 0 | 300
| Task | 3.1.7 | Sojourn Tech. Assistance & Promotion: Assist water trail managers & partners in planning and promoting educational sojourns and paddling opportunities. | Citizen stewardship and advocacy is fostered through connecting people with the resources of the water trails. |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 3.1.8 | SGP Sojourn: Plan and conduct one paddle-peddle event (1 or 2-day.) | Citizen stewardship and advocacy is fostered through connecting people with the resources of the water trails. |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | WT | Paddle-Peddle event: River & Trail Guides, Medic | [29 empty] | 1 | 900 | 900 | 900 | [21 empty] | 0 | 900
| Dir Cost | WT | Paddle-Peddle event: Meals, supplies, signage, tees, etc. | [29 empty] | 50 | 30 | 1500 | 1500 | [21 empty] | 0 | 1500
| Dir Cost | WT | Paddle-Peddle event: Fees & Insurance, Facilities, Transportation. | [29 empty] | 1 | 600 | 600 | 600 | [21 empty] | 0 | 600
| Dir Cost | WT | Travel Expenses (Staff Mileage & Misc.) for TYTP and Paddle-Peddle Events | [29 empty] | 1000 | 0.5 | 500 | 500 | [21 empty] | 0 | 500
| Task | 3.1.9 | Water Trails Promotion: Generate articles, success stories, profiles, etc., for publicity & promotion of WT work in SGP newsletters, website, and outreach events. | Water Trails will be recognized as regional assets which attract visitors and investment. Communities are seen as destinations instead of a point. |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 3.1.10 | Water Trails Progress Reporting: Staff collaboration & reporting on objectives, tasks, & outcomes: staff meetings, timesheets, managing/documenting metrics of success & accomplishments, managing project expenditures & deliverables. | SGP Board & Staff, partners & stakeholders will have timely and accurate reporting that shows accountability for project goals, accomplishments & expenditures. |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 3.1.11 | Water Trails Grant Administration: General administration of WT Program Grant Agreements. | Funders will have timely reporting that shows accountability for project goals, accomplishments & expenditures. |  |  | Kassia | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 3.1.12 | Water Trails Work Plan: Development of an annual work plan and resources for next year's WT Program. Work on WT-related SGP Strategic Planning. | The plan will guide program initiatives. Reources will be available to run the program |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | WT | Meeting & conference Travel Expenses (Staff Mileage & Misc.) | [29 empty] | 500 | 0.5 | 250 | 250 | [21 empty] | 0 | 250
| Objective | 3.2.0 | Support the planning of the Susquehanna River Sports Park | A collaborative group of partners has reached a design agreement to accommodate the River Sports Park and is moving ahead with land acquisition negotiations. |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501 | 800.5 | 1050 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | 0
| Task | 3.2.1 | Convene Partners - Refine Project Development Design and Timeline |  |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 3.2.2 | Develop Funding Strategy |  |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | WT/SRSP | RiverSports Park Project Manager - Contract Position
| Dir Cost | WT/SRSP | RiverSports Park Project Travel Expenses (Staff Mileage & Misc.) | [29 empty] | 500 | 0.5 | 250 | 250 | [21 empty] | 0 | 250
| Dir Cost | WT/SRSP | RiverSports Park Project Printing Expenses (Project Profile, maps, etc.) | [29 empty] | 1 | 800 | 800 | 800 | [21 empty] | 0 | 800
Susquehanna Greenway Partnership Plan of Work Fiscal Year 2015 - 2016
Goals, Objectives, Tasks |  | # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Desired Outcome | Output Timeframe | Status of Completion | Lead Responsibility | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Staff Costs | Other Costs # Units | Other Costs Cost/Unit | Total Other Costs | TOTAL EXPENSE | DCNR 19 | DCNR 20 | DCNR 21 | DCNR Peer Contracts | ARC | CBC 2015 | CBC 2016 | FPW 2014 | POWR 2016 | PA Humanities Council | Central Susq Commun Fdn | FPW 2015 | Luzerne Fdn | NGOs Civic Orgs | Other Corporate Donations | Williams Transco | PA Realtors Assoc | Individual Donations | Board Member Donations | Program Fees | Mdse. Royalties | Total | Balance Needed | In-Kind Reduction of Cash Expense | In-Kind match of hours/service | In-Kind Source
| Management and General | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12700 | 12700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12700 | 0 | 0
| Goal | Build a sustainable organization that is capable of achieving it mission in a responsible manner | [55 empty] | 0 | 0
| Objective | 4.1.0 | Legal Record Keeping and Insurance |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0
| Task | 4.1.1 | Legal Records: Processing & maintenance of legal records. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.1.2 | Insurance: Review & facilitate insurance coverage for Board, Staff and Volunteers |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | M&G | Direct Cost for D&O Liability and General Liability Insurance, including for volunteers. | [29 empty] | 1 | 3000 | 3000 | 3000 | [21 empty] | 0 | 3000
| Objective | 4.2.0 | SGP Organizational & Fiscal Administration | SGP provides clear accountability to stakeholders, thereby building trust to support contributions |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0
| Task | 4.2.1 | SGP Work Plan: Manage and maintain the current fiscal year SGP Plan of Work. Prepare an annual SGP Plan of Work for the next year. | SGP Board and Staff are focused on the most important work to advance the Susquehanna Greenway in a financially responsible manner |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.2.2 | SGP Budget: Manage and maintain the current fiscal year SGP Operating Budget. Prepare an annual SGP Operating Budget for the next year. | SGP Board and Staff are focused on the most important work to advance the Susquehanna Greenway in a financially responsible manner |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.2.3 | Bi-Monthly Bookkeeping: Accounts Receivable & Accounts Payable processing, including all related communications & reporting to Exec. Director and Treasurer. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.2.4 | Monthly Accounting: FNB Bank Statement Reconciliation, FNB Credit Card Acct Reconciliation, Blackbaud Merchant Services fee processing, QBA/eTapestry Revenue Reconciliation. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.2.5 | Yearly Accounting: End of Fiscal Year reporting of program and project-specific revenue, expenses & other assets and liabilities for projecting next year's SGP Plan of Work & Budget. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.2.6 | Tax Return Information: End of Fiscal Year reporting of revenue, expenses, receivables, payables, other assets & liabilities, expenses breakdown by Functional Category and General Company Information for tax return preparation. Coordinate final Federal And State tax return filings with contracted accountants & SGP Directors. | SGP meets IRS & State of PA reporting requirements; provides clear accountability to stakeholders, thereby building trust to support contributions |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | M&G | Bank & Credit Card Processing Fees | [29 empty] | 1 | 1000 | 1000 | 1000 | [21 empty] | 0 | 1000
| Dir Cost | M&G | Direct Costs of Preparation of Form 990, including CPA consultation services | [29 empty] | 1 | 3500 | 3500 | 3500 | [21 empty] | 0 | 3500
| Objective | 4.3.0 | Financial Reporting | SGP Board and Stakeholders are assured that our accounting systems are accurate and correct; thereby building trust to support contributions |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task | 4.3.1 | Monthly SGP Fiscal Book: Monthly generation of printed fiscal record book: SGP Financial Statements. Review meetings with Exec. Director & Treasurer. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.3.2 | SGP Treasurer's Report: Quarterly generation of SGP Treasurer's Report, including reconciliation w. Fundraising Report. Review meetings with Exec. Director & Treasurer. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Objective | 4.4.0 | Human Resources, incl. SEDA-COG organizational costs for contracted administrative & payroll services. Staff training and development | Proper legal requirements are met to secure staffing needed to run organization and do program work |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0
| Task | 4.4.1 | SGP Staff Timesheets: Yearly generation and ongoing maintenance of SGP Staff Timesheet application. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.4.2 | SGP Staff Support: Maintain Staff bios and organizational chart. Coordinate Staff, Intern & Volunteer administrative requirements and needed equipment & support services. Facilitate General Office & Staff Organization and Collaboration. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | M&G | Direct Cost of payroll services for SEDA COG employees | [29 empty] | 1 | 4000 | 4000 | 4000 | [21 empty] | 0 | 4000
| Objective | 4.5.0 | Executive Governance Committee: Tasks & expenses related to Executive Administration & Board Development | Strong leadership and management of the organization |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task | 4.5.1 | Exec Governance Committee: Convene 4 meetings of the Executive Governance Committee. Perform task & admin. support to the Committee & committee meetings. |  |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.5.2 | Strategic Plan: Annual review of Strategic Action Plan & recommendation to full board |  |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.5.3 | Board Development: Annual review of board development needs |  |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Objective | 4.6.0 | Board Meetings and Board Member Support, including tasks & expenses related to Governance and Legal, Board Development, Board Member Handbook. | Strong leadership and management of the organization |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0
| Task | 4.6.1 | Board Meeting Support: Create Board of Directors Meeting Schedule, Meeting Content. Create & Distribute Meeting Support Packet. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.6.2 | Board Meeting Participation: Recording and distribution of meeting minutes, execution of meeting Action Items, and Misc. Meeting Followup. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 4.6.3 | Board Handbook: Maintain Current Board Member Handbook: Director hardcopies, local digital files, web site page. Distribute Handbook updates & generate additional Handbooks as needed. |  |  |  | Barbara | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | M&G | M&G Meeting Expenses for Board (Catering, luncheons, etc.) | [29 empty] | 80 | 15 | 1200 | 1200 | [21 empty] | 0 | 1200
Susquehanna Greenway Partnership Plan of Work Fiscal Year 2015 - 2016
Goals, Objectives, Tasks |  | # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Desired Outcome | Output Timeframe | Status of Completion | Lead Responsibility | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Staff Costs | Other Costs # Units | Other Costs Cost/Unit | Total Other Costs | TOTAL EXPENSE | DCNR 19 | DCNR 20 | DCNR 21 | DCNR Peer Contracts | ARC | CBC 2015 | CBC 2016 | FPW 2014 | POWR 2016 | PA Humanities Council | Central Susq Commun Fdn | FPW 2015 | Luzerne Fdn | NGOs Civic Orgs | Other Corporate Donations | Williams Transco | PA Realtors Assoc | Individual Donations | Board Member Donations | Program Fees | Mdse. Royalties | Total | Balance Needed | In-Kind Reduction of Cash Expense | In-Kind match of hours/service | In-Kind Source
| Fundraising | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0
| Goal | To provide the financial and in-kind resources needed to support the programs and mission of SGP | [55 empty] | 0 | 0
| Objective | 5.1.0 | Improve the engagement and effectiveness of Board Members in fundraising to meet goals for our annual budget and operating reserve; and to ensure the financial stability of SGP. | 100% Board Giving achieved and $8,000 in unrestricted revenue received. | FY 2015-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task | 5.1.1 | Development & Outreach Committee: Convene 6 meetings of the Development & Outreach Committee. Perform task & admin support to Development Committee re. appointing board leadership & achieving board giving goals. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 5.1.2 | Support for Board Members' Fundraising Activities: Engage board members in identifying, cultivating, and soliciting contributions. Meet with each board member individually to discuss fundraising goals and donor identification, cultivation and solicitation strategies. Plan special tasks to potential major donors & the identification of business donors and sponsors. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 5.1.3 | Provide Board Member Fundraising Materials: Establish schedule for donor identification, cultivation and solicitation. Create fundraising materials for Board Member use. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 5.1.4 | SGP Board Member Donations: Manage SGP Board Member personal fundraising commitments, send appeal letters to current and past Board members, make follow-up & thank-you calls to current and past Board Members. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Objective | 5.2.0 | Increase unrestricted revenue received from Individual Donors. | Individual Donor Contributions increased to $20,000 (100 new members and total 350 members) | FY 2015-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 7000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0
| Task | 5.2.1 | Individual Donor Fundraising: Manage & distribute individual donor renewal notices, acquisition letters, e-letters, Progress Report, social media & newsletter messages, acknowledgments, thank-you's, etc. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | FR | Direct expenses for 2 Individual Memb Appeals & 4 Renewals (Graphics, Printing, Postage.) | [29 empty] | 1 | 7000 | 7000 | 7000 | [21 empty] | 0 | 7000
| Objective | 5.3.0 | Increase unrestricted revenue received from Business Donors. | Business Donor Contributions increased to $45,000. | FY 2015-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0
| Task | 5.3.1 | Business Prospect Research: Identify business donor prospects for corporate campaign and research giving history. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 5.3.2 | Business Donor Fundraising: Manage & distribute business donor renewal notices, solicitation letters, e-letters, Progress Report, social media & newsletter messages, acknowledgments, thank-you's, etc. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Task | 5.3.3 | Business Donor Conferencing: Manage & participate in contact followups with businesses: phone calls, in-person meetings. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Dir Cost | FR | Direct expenses for 2 Business Memb. Appeals & 4 Renewals (Graphics, Printing, Postage.) | [29 empty] | 1 | 5000 | 5000 | 5000 | [21 empty] | 0 | 5000
| Objective | 5.4.0 | Provide Support for Grant Funding from Foundations & Government Sources |  | FY 2015-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task | 5.4.1 | Funding Research: Identify funding/grant programs that match our work plan and projects. |  |  |  | Michele | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
| Objective | 5.5.0 | Increase revenues from Program Service Fees | Contributions from Program Service Revenues | FY 2015-16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task | 5.5.1 | Program Revenue Development: Identify programs & projects that match our work plan and yield program service revenues, i.e. educational workshops, sojourns & events. |  |  |  | Trish | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 | 0 | [21 empty] | 0 | 0
|  |  | Monthly Office Expense (SEDA COG) | [28 empty] | 0 |  |  | 36300 | 36300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36300 | 0 | 0
| Dir Cost | SC/OE | TRAVEL/VEHICLE EXPENSE | [29 empty] | 1 | 800 | 800 | 800 | [21 empty] | 0 | 800
| Dir Cost | SC/OE | OFFICE RENT | [29 empty] | 1 | 12000 | 12000 | 12000 | [21 empty] | 0 | 12000
| Dir Cost | SC/OE | POSTAGE | [29 empty] | 1 | 1000 | 1000 | 1000 | [21 empty] | 0 | 1000
| Dir Cost | SC/OE | PRINTING | [29 empty] | 1 | 1500 | 1500 | 1500 | [21 empty] | 0 | 1500
| Dir Cost | SC/OE | PHONE, incl. Staff Cellular | [29 empty] | 1 | 1400 | 1400 | 1400 | [21 empty] | 0 | 1400
| Dir Cost | SC/OE | EQUIPMENT | [29 empty] | 1 | 3600 | 3600 | 3600 | [21 empty] | 0 | 3600
| Dir Cost | SC/OE | COMPUTER SUPPORT | [29 empty] | 1 | 6000 | 6000 | 6000 | [21 empty] | 0 | 6000
| Dir Cost | SC/OE | SUPPLIES | [29 empty] | 1 | 1500 | 1500 | 1500 | [21 empty] | 0 | 1500
| Dir Cost | SC/OE | REFERENCE MATERIAL | [29 empty] | 1 | 300 | 300 | 300 | [21 empty] | 0 | 300
| Dir Cost | SC/OE | INSURANCE | [29 empty] | 1 | 1600 | 1600 | 1600 | [21 empty] | 0 | 1600
| Dir Cost | SC/OE | AUDIT | [29 empty] | 1 | 1800 | 1800 | 1800 | [21 empty] | 0 | 1800
| Dir Cost | SC/OE | MISCELLANEOUS | [29 empty] | 1 | 800 | 800 | 800 | [21 empty] | 0 | 800
| Dir Cost | SC/OE | INTERN/CONTRACTORS RENT | [29 empty] | 1 | 4000 | 4000 | 4000 | [21 empty] | 0 | 4000
[36 empty] | 0 | [21 empty] | 0 | 0
Goals, Objectives, Tasks |  | # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Desired Outcome | Output Timeframe | Status of Completion | Lead Responsibility | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern | Staff Costs | Other Costs # Units | Other Costs Cost/Unit | Total Other Costs | TOTAL EXPENSE | DCNR 19 | DCNR 20 | DCNR 21 | DCNR Peer Contracts | ARC | CBC 2015 | CBC 2016 | FPW 2014 | POWR 2016 | PA Humanities Council | Central Susq Commun Fdn | FPW 2015 | Luzerne Fdn | NGOs Civic Orgs | Other Corporate Donations | Williams Transco | PA Realtors Assoc | Individual Donations | Board Member Donations | Program Fees | Mdse. Royalties | Total | Balance Needed | In-Kind Reduction of Cash Expense | In-Kind match of hours/service | In-Kind Source
| Total | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6700 | 6700 | 0 | 0 | 0 | 13400 |  |  | 155795 | 169195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169195 | 0 | 0
[32 empty] | Total Projected Revenue (grid below) |  |  |  | 436292 | 16789 | 129660 | 55000 | 44000 | 31029 | 23619 | 5000 | 7962 | 1800 | 8400 | 10000 | 9500 | 3933 | 500 | 40000 | 7500 | 5000 | 20000 | 8000 | 5000 | 3600 | 436292
Projected Revenue for FY 2015-16
[33 empty] | DCNR 19 |  |  |  | 16789 |  | MG funding not awarded, deferred from FY14-15
[33 empty] | DCNR 20 |  |  |  | 129660 |  | Remainder of $200K Grant not expended in FY14-15
[33 empty] | DCNR 21 |  |  |  | 55000 |  | Applied for $286K
[33 empty] | Peer Grants |  |  |  | 44000
[33 empty] | ARC |  |  |  | 31029 |  | Remainder of $45K Grant not expended in FY14-15
[33 empty] | CBC 2015 |  |  |  | 23619 |  | Remainder of $28K Grant not expended in FY14-15
[33 empty] | CBC 2016 |  |  |  | 5000 |  | Based on 50% of expected grant $10,000
[33 empty] | FPW 2014 VSN Funding |  |  |  | 7962 |  | Remainder of $11K Grant not expended in FY14-15
[33 empty] | POWR 2016 |  |  |  | 1800
[33 empty] | PA Humanities for Williamsport Project |  |  |  | 8400
[33 empty] | Central Susq Community Foundation |  |  |  | 10000 |  | Berwick/other Year 1 River Town Tech Assistnce
[33 empty] | Foundation for Pa Watersheds |  |  |  | 9500 |  | $7500 for Property Acquisition Costs, $2000 Convening Grant
[33 empty] | Luzerne Foundation |  |  |  | 3933
[33 empty] | NGOs/Civic Organizations |  |  |  | 500
[33 empty] | Corporate, general |  |  |  | 40000
[33 empty] | Williams Transco |  |  |  | 7500
[33 empty] | PA Realtors |  |  |  | 5000
[33 empty] | Individuals |  |  |  | 20000
[33 empty] | Board Members |  |  |  | 8000
[33 empty] | Program Fees |  |  |  | 5000
[33 empty] | Merchandise Royalties |  |  |  | 3600
[33 empty] | Total Projected Revenue |  |  |  | 436292
[33 empty] | Total Projected Expense |  |  |  | 169195 | Includes AmeriCorps costs, Excludes SGP Staff, Intern Costs, SRSP Contractor
[33 empty] | Projected Change in Net Assets |  |  |  | 267097
[32 empty] | Staff Costs | % of tot |  | Total Other Costs | TOTAL EXPENSE | % of tot | % of tot staff cost | Office Expense Allocation | Total Program/ Project
[27 empty] | Education, Outreach and Promotion |  |  |  |  | 0 | 0% |  | 38970 | 38970 | 23.03% | 0% | 0 | 38970 | [10 empty] | 0 | 0 | 0
[27 empty] | Volunteer Program |  |  |  |  | 13400 | 100% |  | 7200 | 20600 | 12.18% | 100% | 36300 | 56900 | [10 empty] | 126600 | 126600 | 126600
[27 empty] | Bike/Ped Trails Project (SGTA) |  |  |  |  | 0 | 0% |  | 10175 | 10175 | 6.014% | 0% | 0 | 10175 | [10 empty] | -126600 | -126600 | -126600
[27 empty] | River Towns Technical Assistance Program |  |  |  |  | 0 | 0% |  | 33350 | 33350 | 19.71% | 0% | 0 | 33350
[27 empty] | Water Trails Program |  |  |  |  | 0 | 0% |  | 5100 | 5100 | 3.014% | 0% | 0 | 5100 | [21 empty] | In-kind donation against cash expense
[27 empty] | Management and General |  |  |  |  | 0 | 0% |  | 12700 | 12700 | 7.506% | 0% | 0 | 12700
[27 empty] | Fundraising |  |  |  |  | 0 | 0% |  | 12000 | 12000 | 7.092% | 0% | 0 | 12000
[27 empty] | Monthly Office Expense (SEDA COG) | [7 empty] | 36300 | 36300 | 21.45%
[27 empty] | Total |  |  |  |  | 13400 | 100% |  | 155795 | 169195 | 100% | 1 | 36300 | 169195
[20 empty] | Trish | Bridget | Erin | RT Program Coordinator | Alice | Development Associate | Barbara | Kassia | Scarlett | BloomU Interns | Lock Haven Interns | SusqU Intern
[13 empty] | Hourly Rate Used in Work Plan Calculations | [6 empty] | 50.92 | 25 | 20 | 24 | 50 | 20 | 17
[13 empty] | Current Hourly Rate | [6 empty] | 50.92 | 25 | 20 | 24 | 50 | 20 | 17
Other hourly rate
Other hourly rate
[9 empty] | Hours |  | Cost |  | Other hourly rate
AmeriCorps Positions:
|  |  | Education/Outreach Program Assistant - 1600 hours to be split between Erin and Bridget (800 hours each) | [7 empty] | 6700 |  | Totals B/On 1690 hrs * hourly rate | [6 empty] | 86054.8 | 42250 | 14000 | 40560 | 15000 | 33800 | 28730 | [5 empty] | 260394.8
|  |  | River Town Program Assistant - 1600 hours to work community profiles and community engagement of volunteers | [7 empty] | 6700 | [5 empty] | DCNR Project Est |  |  | 77449.32 | 27462.5 | 14000 | 40560 | 15000 | 5633.3333 | 17238 | [5 empty] | 197343.1533
Bloomsburg University Summer EGGS Interns:
|  |  | GIS Intern | [5 empty] | 468 |  | 0
|  |  | River Towns community profiles and engagement | [5 empty] | 468 |  | 0
Lock Haven University Intern:
|  |  | ARC Grant - Community Assessments | [5 empty] | 300 |  | 3600
Susquehanna University Interns:
Susquehanna University Interns:
|  |  | Video Contest and Production - Spring semester for credit to develop contest and script for 2 videos. Summer paid internship to produce 2 videos. | [7 empty] | 5000
[9 empty] | 1236 |  | 22000

## Sheet1
Sample Action Plan Template
| # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Who | By When | Measures of Success | Funding Sources
Focus Area:
Goal
Objective/ Project | 1
Task | 1.1
Task | 1.2
Task | 1.3
Objective/ Project | 2
Task | 2.1
Task | 2.2
Task | 2.3
Objective/ Project | 3 | E
Task | 3.1
Task | 3.2
Task | 3.3
| # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Who | By When | Measures of Success | Funding Sources
Focus Area: Partnerships for Success
Goal | Build a community of people and partners who share our vision for the future and help to implement action items
Objective/ Project | 1 | Strengten Partnerships with local governmental and civic organizations, county planners, transportation planners, State and Federal agencies, non-profit organizations and businesses, to build awareness and support for projects and to ensure integration of plans. |  |  | Our priority projects wiill be incorporated into the plans of partners.
Task | 1.1 | Ask local municipalities and non-profit organizations to adopt vision and assist with projects |  |  | Community partners are aligned with vision and helping with implementation
Task | 1.2 | Ask County Planning Department to incorporate action plan items into County and regional plans |  |  | Increased technical and funding support is available
Task | 1.3 | Ask PennDOT to incorporate bicycle and pedestrian improvement projects in their plans |  |  | Projects are eligible for PennDOT funding
Objective/ Project | 2 | Increase awareness and support for vision and Action Plan among residents and businesse |  |  | More people help to implement projects.
Task | 2.1 | Develop outreach and marketing campaign
Task | 2.2
Task | 2.3
Objective/ Project | 3 | Encourage volunteerism….
Task | 3.1
Task | 3.2
Task | 3.3
| # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Who | By When | Measures of Success | Funding Sources
Focus Area: Improve Riverfront Parks and River Access
Goal | Residents and visitors can easily access to the Susquehanna River and enjoy outdoor recreation.
Objective/ Project | # | Strengthen our parks and recreation commission's ability plan, construct and sustain riverfront parks
Task
Task
Objective/ Project | # | Improve Riverfront Park and create a new river access in riverfront park
Task |  | Develop master park plan for Riverfront Park
Task
| # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Who | By When | Measures of Success | Funding Sources
Focus Area: Improve Walkability and Bikeability
Goal | Resdients and visitors can safely and easily walk and bike to work, school and shopping, and for recreation
Objective/ Project | # | Plan priority bicycle/pedestrian projects that improve connectivity to schools, parks, downtown
Task |  | Install Bike Racks in downtown and parks
Task |  | Hold a Bike Rodeo to train kids bicycle safety
Task |  | Work with the public works department to improve pedestrian crossings and bicycle facilites
Task |  | Conduct Bicycle and Pedestrian Audit
Task |  | Develop Active Transportation Plan
Objective/ Project | # | Create walking loops to encourage healthy living
Task
Task
| # | SMART Objectives SMART = Specific, Measurable, Achievable, Relevant, Time limited and Tasks (Outputs) | Who | By When | Measures of Success | Funding Sources
Focus Area: Grow the Nature-Based Economy
Goal | Natural, recreational and cultural assets are enhanced and support a growing and sustainable economy
Objective/ Project | # | Promote our town as a center for outdoor recreation and culture
Task |  | Develop River Town Brochure
Task |  | Create trip itineraries
Task |  | Develop Community Signage Plan
Objective/ Project | # | Recruit businesses needed to grow the nature-based economy
Task |  | Identify missing businesses and services
Task |  | Work with chamber of commerce and Small Business Develop Center to attract and support entrepreneurs